## Training_Plan
TRAINING SCHEDULE
Information |  |  |  | Document task
Trainee: BKU Students |  |  |  | Practice task
Target: Giving a Design Lab for student via RVC/Cadence/University Collaboration |  |  | ▲ | Due date
No. | Content | Input |  | Output | Apr. 17 |  | May. 08 |  |  | May. 22 |  |  |  | Jun. 05
[5 empty] | 1 |  | 2 |  |  | 3 |  |  |  | 4
1 | - Review LSI Design Flow | - Function Spec (Bound Flasher) |  | - Design Spec |  |  |  | ▲ | May. 10
| - Introduce and explain Function Spec (Bound Flasher) | - Sample Design Spec |  | - Checklist (without result) |  | ▲ | May. 07
| - Explain what's Design Spec, its content base on sample Design Spec | - Sample Checklist |  | - RTL (un-verified) |  | ▲ | May. 07
| - Explain what's Checklist, how to make it base on sample Checklist |  |  | - Testbench |  | ▲ | May. 07
- Separate to 2 team:
+ Team 1: Practice create Design Spec
+ Team 2: Practice create Checklist
2 | - QnA for previous lecture | - How to simulate with XCELIUM 20.03 guideline |  | - Updated Testbench (if necessary) | [6 empty] | ▲ | Jun. 01
| - Explain what's Testbench, its purpose and how to make it |  |  | - RTL (verified) | [6 empty] | ▲ | Jun. 01
| - Introduce Cadence simulation tool (XCELIUM 20.03) |  |  | - Checklist (with result) | [6 empty] | ▲ | Jun. 01
| - Practice simulation base on Bound Flasher RTL |  |  | - Updated Design Spec (if necessary) | [6 empty] | ▲ | Jun. 01
3 | - QnA for previous lecture | - How to synthesize with RTL Compiler GENUS 19.1 guideline |  | - Netlist (without timing violation) | [8 empty] | ▲ | Jun. 04
| - Introduce Logic Synthesis, Synthesis constraint, show example Netlist schematic | - Sample synthesis constraint |  | - Synthesis report | [8 empty] | ▲ | Jun. 04
| - Introduce Cadence RTL Compiler synthesis tool (GENUS 19.1) |  |  | (constraint, maximum speed, area)
- Practice synthesis base on Bound Flasher RTL, how to solve timing violation
4 | - QnA for previous lecture | - How to use Conformal-LEC guideline |  | - FV report | [10 empty] | ▲ | Jun. 15
| - Introduce Logic Equivalent Check and its purpose | - Sample FV report
- Introduce Cadence Conformal-LEC tool (CONFRML20.1)
- Practice execute Conformal-LEC base on Bound Flasher RTL and Netlist
- Guide to debug by GUI (if enough time)